## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US-01 | Implement FastAPI backend with Uvicorn and WebSocket routing for real-time audio translation. | MUST HAVE | -- | Developer Team | 3- Completed
1 | 2 | US-02 | Integrate custom-trained Whisper ASR model for English/Hindi transcription. | MUST HAVE | US-01 | Developer Team | 3- Completed
2 | 2 | US-03 | Implement NLLB-200 translation model with caching for fast multilingual translation. | MUST HAVE | US-02 | Developer Team | 3- Completed
2 | 2 | US-04 | Add gTTS-based speech synthesis with asynchronous audio playback. | SHOULD HAVE | US-03 | Developer Team | 3- Completed
3 | 3 | US-05 | Create real-time microphone translation flow using sounddevice and chunk processing. | MUST HAVE | US-04 | Developer Team | 3- Completed
3 | 3 | US-06 | Capture system audio using FFmpeg Stereo Mix and integrate into real-time pipeline. | MUST HAVE | US-05 | Developer Team | 3- Completed
4 | 4 | US-07 | Implement upload support for audio/video files and process via ASR → Translation → TTS pipeline. | SHOULD HAVE | US-06 | Developer Team | 3- Completed
4 | 4 | US-08 | Build responsive UI for Live, OTT, and File translation modes. | SHOULD HAVE | US-07 | Frontend Team | 3- Completed
5 | 5 | US-09 | Implement WebSocket client logic for receiving transcription and translation updates in real time. | MUST HAVE | US-08 | Frontend Team | 3- Completed
5 | 5 | US-10 | Final deployment, model warm-up, caching, and latency optimizations for production-ready performance. | SHOULD HAVE | US-09 | Deployment team | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 45 | 4 | 5 | 4 | 6 | 5 | 6 | 2 | 4 | 3 | 4 | 0 | 0 | 1 | 1
SPRINT 1 BACKLOG
US001 | TI001 | Speech Recognition and Data Collection | 2025-10-05 | 2025-10-15 | Sushant Kumar Sinha | Others | 3- Completed | 12 | Day 1: 1; Day 2: 1; Day 4: 2; Day 5: 2; Day 6: 2; Day 7: 1; Day 9: 2; Day 10: 1
US002 | TI002 | Translation Model Development and Training | 2025-10-16 | 2025-11-01 | Janvi, kevin varghse J | Build | 3- Completed | 10 | Day 2: 2; Day 5: 1; Day 6: 1; Day 8: 2; Day 10: 2; Day 13: 1; Day 14: 1
US003 | TI003 | Real-time Speech-to-Speech Integration | 2025-11-02 | 2025-11-11 | Sushant Kumar Sinha,Kevin Varghese J,Janvi | Coding | 3- Completed | 12 | Day 1: 1; Day 3: 2; Day 4: 2; Day 6: 2; Day 7: 1; Day 8: 2; Day 9: 1; Day 10: 1
US004 | TI003 | Deployment and Embedding into OTT Platform | 2025-11-12 | 2025-11-16 | Sushant Kumar Sinha,Kevin Varghese J,Janvi | Integration Test | 3- Completed | 11 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2; Day 5: 2; Day 6: 1
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | In Data Collection, Datasets were too large to preprocess. | Downloaded small datasets for Hindi and English. Used Kaggle Hindi dataset (3843 clips) and LJ Speech dataset
Sprint 1 | Day 5 | Audio format compatibility issues with different file types | Integrated FFmpeg for universal audio format conversion and standardization.
Sprint 2 | Day 3 | Training Machine - Limited GPU memory for ASR model training | Used smaller Whisper-Base model and implemented batch processing to fit within memory constraints.
Sprint 2 | Day 7 | Poor Hindi ASR accuracy with pre-trained models. | Fine-tuned Whisper model on Hindi dataset, achieving 88% accuracy improvement.
Sprint 3 | Day 2 | High latency in real-time translation pipeline. | Implemented threading + async I/O for parallel processing, reduced latency to 3.2 seconds.
Sprint 3 | Day 6 | NLLB translation model producing inaccurate results for complex sentences. | Added text preprocessing and context preservation techniques to improve translation quality.
Sprint 4 | Day 1 | WebSocket connection drops during real-time audio streaming | Implemented automatic reconnection logic and buffer management for stable connections.
Sprint 4 | Day 4 | TTS audio output had robotic voice and poor quality. | TTS audio output had robotic voice and poor quality.
Sprint 5 | Day 3 | Memory leaks during long speech processing sessions. | Implemented memory monitoring and garbage collection, reducing memory usage by 25%.
Sprint 5 | Day 5 | Real-time captions not syncing with audio playback | Implemented audio-video synchronization and timing controls.
Sprint 6 | Day 4 | Three-mode interface (Live Mic, OTT, File) confusing for users | Redesigned UI with clear mode selection and intuitive icons
Sprint 7 | Day 7 | File upload feature not working with backend API. | Fixed file handling and implemented proper MIME type validation.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-10-05 | 2025-10-15 | Sushant Kumar Sinha | Dataset collection | Manual record keeping | Research datasets | collected datasets from different sources
2 | 1 | 2025-10-05 | 2025-10-15 | kevin varghse J | Model searching and selection | Random model selection | Whisper model research | Implemented performance metrics
3 | 1 | 2025-10-05 | 2025-10-15 | Janvi | Dataset quality validation | Manual data checks | Research on audio datasets | Created data validation checklist
4 | 2 | 2025-10-16 | 2025-11-01 | Sushant Kumar Sinha | Audio preprocessing | Manual file handling | Backend setup | Automated audio processing pipeline
5 | 2 | 2025-10-16 | 2025-11-01 | kevin varghse J | FFmpeg integration | Single format support | Audio testing | Implemented multi-format support
6 | 2 | 2025-10-16 | 2025-11-01 | Janvi | Model training documentation | Unrecorded experiments | Performance tracking docs | Created model training journal
7 | 3 | 2025-11-02 | 2025-11-11 | Sushant Kumar Sinha | Integration testing | Module isolation | End-to-end testing | Completed pipeline integration
8 | 3 | 2025-11-02 | 2025-11-11 | kevin varghse J | ASR model tuning | Default parameters | Accuracy improvement | Achieved 88% Hindi ASR accuracy
9 | 3 | 2025-11-02 | 2025-11-11 | Janvi | Translation optimization | Word-by-word translation | Context preservation | Improved translation quality
10 | 4 | 2025-11-12 | 2025-11-16 | Sushant Kumar Sinha | Web interface development | Complex UI designs | Minimalist approach | Built intuitive web interface
11 | 4 | 2025-11-12 | 2025-11-16 | kevin varghse J | Real-time optimization | High latency processing | Stream processing | Reduced latency to 3.2 seconds
12 | 4 | 2025-11-12 | 2025-11-16 | Janvi | Project report documentation | Last-minute reporting | Continuous documentation | Prepared final project report