## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Developer Team | 09/10/25 | Audio preprocessing step fails to remove background noise for multilingual inputs. | Sprint 1 | Developer Team | Logical | Updated noise-reduction filter and reprocessed sample inputs. | 07/10/25 | Closed | Preprocessing now consistent across all languages.
2 | Developer Team | 17/10/25 | Speech-to-Text misrecognizes Hindi speech during background noise. | Sprint 2 | Developer Team | Logical | Updated acoustic model and retrained with noisy datasets. | 16/10/25 | Closed | Accuracy improved significantly.
3 | Developer Team | 20/10/25 | Translation output has 3–4 seconds delay for Tamil Language. | Sprint 2 | Developer Team | Logical | Updated acoustic model and retrained with noisy datasets. | 18/10/25 | Closed | Accuracy improved significantly.
4 | Developer Team | 23/10/25 | First 1–2 seconds of translated audio missing during continuous speech. | Sprint 3 | Developer Team | Logical | Increased buffer window and synchronized timestamps. | 21/10/25 | Closed | No clipping observed.
5 | Developer Team | 28/10/25 | BLEU score too low for fast-paced speech. | Sprint 3 | Developer Team | Logical | Added movie-specific dataset; retraining ongoing. | 26/10/25 | Open | Awaiting evaluation.
6 | Deployment Team | 16/11/25 | OTT feed fails to embed translated audio for Malayalam. | Sprint 4 | Deployment Team | Logical | Fixed codec mapping and updated audio. | 14/11/25 | Closed | Working across all languages.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others